## Sheet1
Number | Phase | User Stories | Acceptance Criteria | Priority | Time Estimation | Done | Time Took
1 | MVP | As a user, I want to upload a photo of 1 person, so that I can analyse it | Must be a photo of 1 face Can upload locally Saves locally | 1 | 1 | x | 30
2 | MVP | As a user, I want my photo to be analysed of 1 person, so that I can find out an emotion score | AJAX request to emotion API of 1 person Gets back JSON data | 1 | 3 | x
3 | MVP | As a user, I want my analysed emotion picture to be displayed in a graph, so that it is easy to understand | Parse JSON data Extract emotions Static spider diagram with emotions | 1 | 7 | x
4 | V1 | As a user, I want to upload a photo of multiple people, so that I can analyse it | AJAX request to emotion API with muliple faces Gets back JSON data | 2 | 2 | x | 1
5 | V1 | As a user, I want my photo to be analysed of multiple people, so that I can find out an emotion score | Parse JSON Data Extract & Average emotions Static graph | 2 | 3
6 | V1 | As a user, I want to be able to activate my webcam, so that I can see the picture I want to take | Start webcam Laptop webcam activated Display live feed | 2 | 4
7 | V1 | As a user, I want to be able to turn my webcam off and stop the feed, so that I have control over my data analysis | Stop Webcam Stop's calls to API | 2 | 1
8 | V1 | As a user, I want to use my webcam to take the pictures, so that is is relevant live data | Take a pic button which takes a snapshot Stores snapshot locally Sends to API | 2 | 6
9 | V1 | As a user, I want a picture to be taken from my webcam in a given interval so that I can have real-time data | Start button Takes snapshot automatically every 10s rerenders graph automatically stop button | 2 | 7.5
10 | V2 | As a user, I want my analysed crowd to be displayed in a positive index graph, so that I can track developments in positive emotion over time | Store data (session/database) Positive index rules defined Create index (apply rules to data) Plot real-time graph | 3
Beyond V1
1 |  | Various graphs for different metrics
2 |  | Multiple cameras
3 |  | general office/place/country happiness
4 |  | playlist selector
5 |  | lighting colour selector
6 |  | emoji stuff
7 |  | user external camera
To Google
Storing API key in heroku (front-end)
React
data visualisation (react/spider diagram)